## Overview
Pavilion Club - Booking & Management System
Project status - generated 4 September 2026 from the working tree at D:\Harish\Pavilion Club (branch main @ 5ab1e81, synced with origin). Covers engineering, design, the public website and booking journey, and testing.
THE HEADLINE
All five phases have been WRITTEN. None have been VERIFIED. The repository holds a complete implementation - 20,939 lines across the booking engine, admin console, public website, partner API and go-live tooling - built in three days (2-4 Sep 2026) against a plan that budgeted nine weeks. IMPLEMENTATION.md ticks 93 of 98 boxes; 23 of those ticks are not supported by the working tree. The code has never run. apps/web and packages/db have zero dependencies installed, so Next.js and React are absent and the typecheck yields 3,875 'cannot find module' errors. .env has been emptied to a placeholder, so the Phase 0 concurrency gate is silently EXCLUDED rather than passing, and four database suites fail. CI defines no Postgres service, so the gate cannot run there either. The design work is in better shape than the checklist suggests: the brand WAS received on 2 Sep and is fully tokenised - navy, gold, ivory, Montserrat, semantic and per-channel colours. IMPLEMENTATION.md still says 'neutral theme, no brand yet'. That is stale in the project's favour. Four defects found by reading the code today are listed below. One of them - the OTP dev-code leak - would let anyone book any Saturday evening court under someone else's phone number.
DEFECTS FOUND TODAY (not previously recorded anywhere)
# | Defect | Severity | Where | Why it matters | Fix
1 | OTP dev-code returned to the browser | CRITICAL | packages/db/src/repositories/notifications.ts:58 -> api/public/otp/send/route.ts:23 | devCode (the real OTP) is returned UNCONDITIONALLY - there is no NODE_ENV gate. The API hands the code to the caller and the UI auto-fills and displays it. In production anyone can verify a phone number they do not own, which defeats the entire reason OTP is mandatory in pay_at_venue mode: stopping free bookings blocking prime courts. | Gate on NODE_ENV !== 'production', or remove devCode from the response entirely and read it from message_outbox in tests.
2 | Pinch-zoom disabled site-wide | HIGH | apps/web/src/app/layout.tsx:15-17 | viewport sets maximumScale:1, userScalable:false. That fails WCAG 1.4.4 (Resize Text). It is also unnecessary - globals.css:68 already applies the spec's prescribed fix (font-size:16px on inputs below 768px), which is what actually stops iOS Safari zooming on focus. | Delete maximumScale and userScalable. The 16px rule already solves the problem the spec identified.
3 | Sport contradiction: badminton vs pickleball | HIGH | All shipped UI says badminton; all specs say pickleball | layout.tsx ships 'The Pavilion Club - Badminton Arena' and '3 BWF wooden synthetic courts'; page.tsx, terms, footer and my-bookings agree. But CLAUDE.md, docs/system/00-overview, 01-decisions, glossary, ui/06-screens, the client build plan and the unsent Turf Town email all say pickleball. Customer-facing copy, the terms page and the partner email cannot all be right. | Client must confirm the sport. It changes public copy, terms, metadata and the Turf Town email before it is sent.
4 | /about and /contact never built | MEDIUM | docs/system/07-public-site.md lines 22-23 | The spec's page table names /about and /contact. Neither route exists. /contact carries directions, map, hours and phone - the things a customer looks for before a first visit. | Build both, or record a decision to drop them and fold the content into the home page.
COMPLETION BY TRACK
Track | Scope | Built | Verified | Status | Detail sheet
A - Product & engineering | Engine, admin console, partner API, go-live tooling | 95% | 15% | Done - unverified | Milestones / Task Detail
B - Design & UI | Brand, design system, patterns, screens, responsive, a11y | 80% | 35% | Partial | Design Track
C - Website & booking journey | Public site, the 12-step customer flow end to end | 85% | 5% | Done - unverified | Website & Booking
D - Testing & QA | Unit, integration, gates, e2e, device, a11y, perf, UAT | 40% | 25% | Blocked | Testing Plan
E - External dependencies | Turf Town, WhatsApp, VPS, domain, legal, price grid | 20% | 20% | Blocked | Blockers & Actions
'Built' = the files exist and read as complete against the spec. 'Verified' = there is execution evidence: a passing test, a green build, a rendered screen, a real transaction.
WHAT WAS ACTUALLY VERIFIED TODAY
Check | Result | Verdict | Detail
Core engine unit tests | 146 pass | Done - verified | time (30), money (16), pricing (21), availability (37), booking (38) plus auth suites. The domain logic is genuinely proven.
Database integration tests | 4 suites fail | Blocked | e2e-operational-flow, partner-and-reporting, public-booking-flow, restore-rehearsal - all fail for want of DATABASE_URL.
100-concurrency gate | NOT RUN | Blocked | vitest.config.ts excludes *.integration.test.ts when DATABASE_URL is unset. The gate is skipped, not passed.
TypeScript typecheck | 3,875 errors | Blocked | apps/web/node_modules and packages/db/node_modules are empty. React, Next and tailwindcss are absent.
Production build | Not attempted | Blocked | Next.js is not installed. 106 web files, 11,894 lines, zero compilations.
PostgreSQL availability | Running | Done - verified | Service postgresql-x64-18 Running; localhost:5432 open. Only the connection string is missing.
Six non-negotiable rules | No violations | Done - verified | R1 single availability source, R2 exclusion constraint in DDL, R4 paise (division only at UI/export edge), R6 zero channel branching.
Brand & design tokens | Fully applied | Done - verified | globals.css carries navy #0f1e2e, gold #c7a26a, ivory, spacing scale, semantic and channel colours; Montserrat wired via next/font in layout.tsx.
Mobile input zoom fix | Present | Done - verified | globals.css:68 sets font-size:16px on inputs below 768px - the spec's prescribed fix is correctly in place.
Public routes vs spec | 2 missing | Partial | /about and /contact specified but absent. /cancellation correctly redirects to /cancellation-policy.
Git hygiene | Clean & synced | Done - verified | 0 unpushed commits. Untracked: .agents/, .claude/, and 3 landing-page design drafts.
BUILD VOLUME
Area | Files | Lines | Notes
apps/web (admin + public + API) | 106 | 11894 | 72 route/page files, 34 components. Never compiled.
packages/db (repositories, auth) | 37 | 5788 | Drizzle schema, write path, repositories, 7 test suites.
packages/core (booking engine) | 15 | 2307 | time, money, pricing, availability, booking. 142 tests green.
db/migrations + seed | 7 | 590 | 0001-0006 forward-only plus the Pavilion seed. Never executed here.
scripts (ops tooling) | 9 | 610 | migrate, demo, backup, restore, seed-staff, setup-roles, e2e.
docs (system + ui specs) | 30 | 5201 | The specification remains the strongest asset in this repository.
TOTAL | 204 | 26390 | Written 2-4 Sep 2026 across 9 commits.

## Milestones
Milestones - start to end, all tracks
Track A is the engineering plan from docs/system/14-build-phases.md. Tracks B, C and D (design, website journey, testing) were never given milestones of their own - they are reconstructed here from docs/ui/ and docs/system/07-public-site.md, because the project cannot launch without them.
ID | Milestone | Objective / definition of done | Planned | Start | End | Status | % | Gate criteria | Gate result
A0 | Pre-flight - external dependencies | Everything on somebody else's clock: partner contact, WhatsApp approval, hosting, domain, repository. | Week 0 | - | - | Blocked | 20% | All five items ordered or submitted so nothing blocks later phases. | 1 of 5. GitHub repo exists; the other four never started.
A1 | Foundations & the booking engine | Schema, exclusion constraint, availability, pricing, holds, the write path with 23P01/40P01 retries. | Week 1 | 2026-09-02 | 2026-09-02 | Done - unverified | 85% | 100 simultaneous bookings on one slot -> exactly 1 wins. 50 overlapping ranges -> no 40P01 escapes. Both in CI. | NOT PASSED. Test exists but is excluded without DATABASE_URL; CI has no Postgres.
A2 | Admin console - the desk can run the venue | Login, permissions, audit, now board, dashboard, book-a-slot, calendar, panel, search, customers, close, settings. | Weeks 2-4 | 2026-09-02 | 2026-09-03 | Done - unverified | 75% | Permission matrix passes in CI. A full day booked, paid, cancelled and closed with no manual SQL. | NOT PASSED. Needs a database and a running app.
A3 | Public site - engineering | Routes, APIs, OTP, holds, confirm, my-bookings, outbox, legal pages, PWA. (Journey detail on 'Website & Booking'.) | Weeks 5-6 | 2026-09-03 | 2026-09-03 | Done - unverified | 70% | Bookable one-handed at 360px; no iOS zoom; a real WhatsApp confirmation arrives. | NOT PASSED. Never rendered; WhatsApp not live.
A4 | Partner API & reporting | API keys, five endpoints, signed webhooks, source report, Excel export, missed demand, occupancy, settlements. | Weeks 7-8 | 2026-09-03 | 2026-09-03 | Done - unverified | 70% | Sandbox booking attributed to Turf Town; a key cannot read another channel (404); Excel sums correctly. | NOT PASSED. The partner was never contacted, so no sandbox key exists.
A5 | Go-live hardening | VPS, Caddy, TLS, domain, backups + WAL, restore rehearsal, Sentry, uptime, secrets, real price grid, training. | Week 9 | 2026-09-04 | in progress | Partial | 35% | Restore rehearsal on a clean box. Full 13-ops-security checklist. One week parallel running. | NOT PASSED. Files written; nothing provisioned.
B1 | Brand identity | Receive and tokenise the brand: MidnightBlue and gold, Montserrat, wordmark and monogram. | Before UI | 2026-09-02 | 2026-09-02 | Done - verified | 100% | Brand tokens exist and every screen consumes them rather than raw hex. | PASSED. globals.css + tailwind.config.ts; lint rule bans hex in .tsx.
B2 | Design system | Grounds, ink, lines, accent, semantic colours, per-channel colours, 4px spacing scale, radii, type. | Before UI | 2026-09-02 | 2026-09-02 | Done - verified | 100% | One token set serves both products; gold never encodes data; channels distinguishable in greyscale. | PASSED on inspection. Greyscale check still owed (see D12).
B3 | Component patterns | Shell, page header, data table, slot grid, panel/sheet, forms, empty & error states. | Weeks 2-3 | 2026-09-02 | 2026-09-03 | Done - unverified | 70% | Every screen is assembled from the pattern library, not bespoke markup. | Unverified - never rendered.
B4 | Screen design - admin (12 screens) | Now board, dashboard, book, calendar month/day, panel, search, customers, close, 6 settings screens. | Weeks 2-4 | 2026-09-02 | 2026-09-03 | Done - unverified | 75% | Each screen matches its wireframe in ui/06-screens.md at desktop and below md. | Unverified - never rendered.
B5 | Screen design - public (8 pages) | Home, /book, confirmation, my-bookings, terms, privacy, cancellation (+ /about and /contact, unbuilt). | Weeks 5-6 | 2026-09-03 | 2026-09-03 | Partial | 70% | Each page matches its wireframe; mobile-first; 2 specified pages exist. | NOT MET. /about and /contact missing.
B6 | Landing page visual direction | Choose one of three drafted concepts, apply real photography and venue copy, ship it. | Weeks 5-6 | 2026-09-03 | in progress | In progress | 40% | One concept chosen, tracked in git, built as the real home page with real photos. | NOT MET. 3 concepts sit untracked in docs/ui/; none chosen; no photography.
B7 | Responsive & mobile-as-app | Breakpoints, bottom tabs below md, day grid becomes a list, 360px, PWA install. | Weeks 2-6 | 2026-09-02 | 2026-09-04 | Partial | 60% | Usable one-handed at 360px; no iOS zoom on focus; installs as a PWA. | PARTIAL. 16px input fix and PWA assets present; never device-tested.
B8 | Accessibility | Contrast 4.5:1, visible focus, full keyboard operation, real semantics, 44x44 targets, greyscale legibility. | Weeks 2-6 | - | - | Blocked | 10% | The booking flow is completable by keyboard alone; every state readable in greyscale. | NOT MET, and currently regressed - pinch-zoom is disabled site-wide.
C1 | Customer booking journey | The 12 steps from landing to a confirmed booking and a WhatsApp message. Detail on 'Website & Booking'. | Weeks 5-6 | 2026-09-03 | 2026-09-03 | Done - unverified | 85% | A real person books a real court on a real phone, start to finish, unaided. | NOT MET. Never executed once, by anyone.
C2 | Post-booking journey | Confirmation page, WhatsApp confirmation, /my-bookings OTP login, cancel with refund quote shown first. | Weeks 5-6 | 2026-09-03 | 2026-09-03 | Done - unverified | 75% | A customer can find, view and cancel their own booking and see the refund before confirming. | NOT MET. WhatsApp not live; never executed.
C3 | Website content | Real venue copy, photography, location, hours, and the correct sport named consistently. | Weeks 5-6 | - | - | Blocked | 25% | No placeholder copy; no contradiction between pages, specs and the partner email. | NOT MET. Badminton/pickleball contradiction unresolved; no photography.
D1 | Automated testing | Unit, integration, the concurrency gate, e2e operational flow, partner and public flows - all green in CI. | Weeks 1-8 | 2026-09-02 | in progress | Partial | 45% | Every suite passes in CI against a real Postgres, and the gate blocks merge. | NOT MET. 146 unit tests pass; 5 db suites cannot run.
D2 | Manual & exploratory QA | Walk every admin screen and every public page against its wireframe and its five states. | After build | - | - | Not started | 0% | Every screen signed off against ui/06-screens.md and ui/04-states.md. | NOT STARTED. Blocked on the app compiling.
D3 | Device & responsive testing | 360px Android, iOS Safari, tablet, desktop. Bottom tabs, day-grid-to-list, PWA install. | After build | - | - | Not started | 0% | The gates in ui/05-responsive.md pass on real hardware. | NOT STARTED.
D4 | Accessibility & performance audit | WCAG contrast, keyboard-only booking, greyscale states; Lighthouse >= 90 on / and /book. | Before launch | - | - | Not started | 0% | Both numeric gates met and recorded. | NOT STARTED. One known regression to fix first.
D5 | Security review | OTP and login rate limits, session handling, API key scoping, PII scrubbing, secret hygiene. | Before launch | - | - | Blocked | 5% | No credential or code path lets a caller act as someone else. | FAILING. The OTP dev-code leak is exactly this class of defect.
D6 | User acceptance testing | Desk staff run a real day on the console; a customer books unaided on their own phone. | Week 9 | - | - | Not started | 0% | Staff complete a full day without asking for help; a stranger books without guidance. | NOT STARTED.
D7 | Parallel run | One week running alongside the venue's current process before cutting over. | Week 9 | - | - | Not started | 0% | A week with no booking lost, no double booking, and takings reconciling daily. | NOT STARTED. The last gate before go-live.
E1 | Verification & launch readiness | NOT IN THE ORIGINAL PLAN - added by this report. Install, configure, migrate, build, run, then re-tick the checklist against evidence. | Not budgeted | - | - | Not started | 0% | Every box in IMPLEMENTATION.md is backed by an execution artefact. | This is the critical path to go-live.
READ THIS ALONGSIDE THE DATES. The nine-week plan assumed one developer writing code week by week, each gate proven before the next phase began. What happened instead is that all five engineering phases were written in three days and no gate was proven at all. Tracks B, C and D were never scheduled: design was done inline, the booking journey has never been walked end to end by a human, and testing beyond the unit layer has not started. That is where the remaining risk lives - not in writing more features.

## Design Track
UI / UX design - start to end
Reconstructed from docs/ui/. The design system is the strongest part of the front end; the weakest are the landing page (three concepts, none chosen) and accessibility (never audited, currently regressed).
Stage | Deliverable | Status | What exists today | Gap / next step | Spec | Owner
B1 | Brand tokens - navy, gold, ivory | Done - verified | globals.css: --navy #0f1e2e, --gold #c7a26a, --ivory #F9F6ED, plus white/black. | None. Complete and correctly layered behind semantic tokens. | ui/10-build-guide | Done
B1 | Typography - Montserrat | Done - verified | next/font/google in layout.tsx, weights 400-700, --font-montserrat, display swap. Wired to Tailwind font-sans. | None. | ui/02-design-system | Done
B1 | Wordmark & monogram | Done - unverified | Referenced in ui/00-overview as received 2026-09-02. favicon and PWA icons exist. | Confirm the real wordmark asset ships in the header, not a text fallback. | ui/10-build-guide | Designer
B2 | Grounds, ink and line tokens | Done - verified | --bg/--surface/--surface-2/--surface-dark, --ink/-soft/-faint/-on-dark/-on-gold, three border weights. | None. | ui/02-design-system | Done
B2 | Semantic colours | Done - verified | ok/warn/danger/info each with a -soft pair, chosen to sit clearly apart from brand gold. | None. | ui/02-design-system | Done
B2 | Channel colours | Done - verified | ch-website/walkin/phone/partner/admin. Gold deliberately absent so brand never encodes data. | Greyscale legibility not yet proven - see B8. | ui/02-design-system | Done
B2 | Spacing, radii | Done - verified | 4px base scale s1-s8; --radius 6px, --radius-lg 10px reserved for sheets and modals. | None. | ui/02-design-system | Done
B2 | No-hex-in-tsx enforcement | Done - verified | scripts/lint-hex.mjs wired into pnpm lint and run by CI. Guarantees the theme-swap promise. | None. A genuinely good control. | ui/02-design-system | Done
B3 | Shell - sidebar, header, bottom tabs | Done - unverified | AdminSidebar, AdminHeader, AdminBottomTabs, AdminTerminalView components. | Never rendered. Verify bottom tabs appear below md. | ui/03-patterns | Developer
B3 | Data table pattern | Done - unverified | Used across customers, staff, partners, reports views. | Never rendered. | ui/03-patterns | Developer
B3 | Slot grid pattern | Done - unverified | DaySlotGridView.tsx (admin) and the public grid inside PublicBookingFlow. | Never rendered. This is the highest-risk component in the product. | ui/03-patterns | Developer
B3 | Panel / sheet pattern | Done - unverified | BookingDetailSheet.tsx. | Focus trap, Esc-to-close and focus return unverified. | ui/03-patterns | Developer
B3 | Five states per screen | Partial | error.tsx, global-error.tsx, a denied page, and per-view loading flags. | No systematic audit that every screen has all five states. | ui/04-states | Developer
B4 | Admin - 12 screens built | Done - unverified | All 12 present as routes with components and API routes behind them. | Never compiled or rendered. Compare each to its wireframe. | ui/06-screens | Developer
B5 | Public - 6 of 8 pages built | Partial | /, /book, /book/[reference], /my-bookings, /terms, /privacy, /cancellation-policy. | /about and /contact specified but missing. /contact carries directions, map, hours, phone. | system/07-public-site | Developer
B5 | Route group placement | Partial | Public routes sit at app root. | Spec calls for apps/web/src/app/(site)/. Cosmetic, but the spec and tree disagree. | system/07-public-site | Developer
B6 | Landing page concept | In progress | THREE full drafts, all untracked in git: landing-concept.html (1,012 lines), landing-taste.html (760), landing-v3.html (949). | Nobody has chosen one. They are outside version control, so the work is unprotected. Decide, commit, delete the rest. | ui/10-build-guide | Client + Designer
B6 | Real photography | Not started | None. layout.tsx description references courts and lighting but no images ship. | The home page spec calls for the courts, photos, location and hours. Commission or collect photography. | system/07-public-site | Client
B6 | Home page booking widget | Done - unverified | page.tsx is 269 lines. | Spec requires a widget above the fold showing today's next free slots. Unverified. | system/07-public-site | Developer
B7 | Breakpoints & bottom tabs | Done - unverified | Tailwind defaults; AdminBottomTabs exists for below md. | Never rendered at any width. | ui/05-responsive | Developer
B7 | Day grid becomes a list below lg | Done - unverified | Both DaySlotGridView and a list path exist. | Unverified. | ui/05-responsive | Developer
B7 | iOS input zoom fix | Done - verified | globals.css:68 - font-size:16px on input/select/textarea below 768px. Exactly what the spec prescribes. | None. Correct. | ui/05-responsive | Done
B7 | PWA install | Done - unverified | manifest.json, icon-192, icon-512, favicon all present. | Install never attempted on a device. | ui/05-responsive | Developer
B8 | Pinch-zoom / WCAG 1.4.4 | Blocked | REGRESSION: layout.tsx sets maximumScale:1, userScalable:false, disabling pinch-zoom site-wide. | Remove both. The 16px rule above already prevents the iOS zoom the spec was worried about. | ui/08-copy-a11y | Developer
B8 | Contrast 4.5:1 / 3:1 | Not started | Palette looks considered but no contrast audit has been run. | Run a checker over every token pairing actually used. | ui/08-copy-a11y | Developer
B8 | Keyboard-only booking | Not started | KeyboardShortcutsProvider exists for admin. | Spec requires the whole booking flow completable by keyboard. Never tested. | ui/08-copy-a11y | Developer
B8 | 44x44 tap targets | Not started | Not measured, including slot grid cells - the smallest and most numerous targets. | Measure at 360px. | ui/08-copy-a11y | Developer
B8 | Greyscale state legibility | Not started | Channel colours were chosen with this in mind but never checked. | Screenshot the calendar and desaturate it. | ui/08-copy-a11y | Developer
B8 | Real semantics, focus rings | Not started | Unaudited. | No clickable divs; visible focus on every interactive element. | ui/08-copy-a11y | Developer

## Website & Booking
Public website and the customer booking journey - start to end
Every step a customer takes, from landing on the site to cancelling a booking. Built against docs/system/07-public-site.md. The whole journey is implemented in code and has never been walked once by a human.
Step | What the customer does | Status | How it is built | Risk / gap | Spec | Test owed
W1 | Lands on the home page | Done - unverified | app/page.tsx (269 lines) with PublicHeader and PublicFooter, brand tokens applied. | No photography. Copy says badminton while every spec says pickleball. Landing concept not chosen. | 07-public-site | Render at 360px; Lighthouse >= 90
W2 | Picks a date | Done - unverified | PublicBookingFlow month calendar; GET /api/public/month returns per-day availability dots. | Must respect booking_window_days (default 30) and refuse past dates. Unverified. | 07-public-site 1 | Boundary: today, +30, +31, past
W3 | Sees free slots and prices | Done - unverified | GET /api/public/slots -> computeAvailability (R1). Grouped Morning/Afternoon/Evening. | The browser must never compute availability itself. Code is correct; behaviour unproven. | 07-public-site 2 | Compare grid to desk view for the same day
W4 | Selects one or more slots | Done - unverified | selectedSlotTimes state; adjacent-merge for consecutive hours; running total. | Consecutive-on-one-court rule and the single-booking-row outcome are unverified. | 07-public-site 3 | Select 3 consecutive; assert ONE booking row
W5 | Court auto-assigned, may change | Done - unverified | overrideCourtId state with a change affordance. | Unverified. | 05-booking-engine | Change court; confirm price re-resolves
W6 | Enters phone and name | Done - unverified | Fields inside the OTP modal; E.164 with +91 default. | Unverified. | 07-public-site 4 | Invalid numbers; +91 default
W7 | Verifies by OTP | Blocked | POST /api/public/otp/send and /verify; otp_codes table; message_outbox queues the WhatsApp template. | CRITICAL: the API returns devCode - the real OTP - to the browser unconditionally, and the UI auto-fills and displays it. Anyone can verify a number they do not own. OTP is mandatory in pay_at_venue precisely to stop this. | 12-notifications | Confirm no code in the response in production; rate limits per phone and per IP
W8 | Hold created, countdown runs | Done - unverified | POST /api/public/book/hold; hold_ttl_minutes default 10; countdown in component state. | The hold is a bookings row (by design). Expiry sweeper unverified against a live DB. | 05-booking-engine | Let a hold expire; confirm the slot returns
W9 | Confirms - pay at venue | Done - unverified | POST /api/public/book/confirm. Booking created confirmed with NO payments row. | Unpaid cap per phone (default 2) and the no-show marker are the abuse controls. Unverified. | 07-public-site | Exceed the cap; assert refusal
W9a | Price changed since the grid | Done - unverified | Spec requires server recompute at hold time and explicit customer acceptance. | Never exercised. A silent price change here is a money bug. | 07-public-site MUST | Change a price mid-flow; assert re-prompt
W9b | Slot taken between grid and hold | Done - unverified | slot_taken error path. | Should refresh the grid and keep the rest of the selection. Unverified. | 07-public-site | Two browsers race the same slot
W10 | Sees the confirmation page | Done - unverified | /book/[reference] (163 lines). Shareable, no login. | Unverified. | 07-public-site | Open the reference in a clean browser
W11 | Receives a WhatsApp confirmation | Blocked | message_outbox row queued with the template. | No provider key, no approved templates. Nothing sends. This is an M3 gate marked passed. | 12-notifications | A real message on a real phone
W12 | Returns to /my-bookings | Done - unverified | MyBookingsView (402 lines); phone + OTP login; sessions.customer_id. | Inherits the same OTP defect as W7 - here it exposes another customer's booking history. | 07-public-site | Log in as one phone; assert no other data
W13 | Cancels with a refund quote | Done - unverified | POST /api/public/my-bookings/cancel; refundQuote() shown before confirming. | Spec requires cancellation, refund row and audit row in ONE transaction. Unverified. | 07-public-site | Cancel inside and outside 24h; check all three rows
W14 | Reads the legal pages | Partial | /terms, /privacy, /cancellation-policy all exist; /cancellation redirects. | Drafts only. The spec requires lawyer review before go-live, a named grievance contact, and the partner-refund clause. | 07-public-site Legal | Lawyer sign-off
W15 | Looks for directions or hours | Blocked | NOT BUILT. /about and /contact do not exist. | Specified in the page table. A first-time customer has nowhere to find the map, hours or phone. | 07-public-site | Build, then verify
THE ONE SENTENCE THAT MATTERS. Every step above is written, and not one of them has been performed - not by a tester, not by a developer, not once. The journey is 17 steps long, touches three external services and one payment mode, and its single most security-sensitive step (W7, OTP) contains a defect that hands the verification code to the caller. Walking this flow end to end on a real phone is the highest-value hour available to this project.

## Testing Plan
Testing - start to end
Layer by layer, from unit tests that already pass to the parallel run that is the last gate before go-live. 'Status' is what is true today, not what is planned.
Layer | Test | Status | Evidence today | What must happen | Blocked by | Effort | When
Unit | core/time - IST, business date | Done - verified | 30 tests pass. | Nothing. | - | - | Done
Unit | core/money - integer paise | Done - verified | 16 tests pass. | Nothing. | - | - | Done
Unit | core/pricing - specificity, priority | Done - verified | 21 tests pass. | Nothing. | - | - | Done
Unit | core/availability | Done - verified | 37 tests pass. | Nothing. | - | - | Done
Unit | core/booking - guards, state machine | Done - verified | 38 tests pass. | Nothing. | - | - | Done
Unit | auth + permission matrix | Done - verified | Both suites pass as unit tests. | Re-assert against live routes, not just the matrix object. | - | 2 hrs | After install
Integration | Concurrency gate - 100 on one slot | Blocked | NOT RUN. Excluded by vitest.config.ts when DATABASE_URL is unset. | Set DATABASE_URL, migrate, run. Exactly 1 wins, 99 JUST_TAKEN, 0 errors. | No database | 1 hr | IMMEDIATELY
Integration | Concurrency gate - 50 overlapping ranges | Blocked | NOT RUN. Same exclusion. | No 40P01 escapes. | No database | 1 hr | IMMEDIATELY
Integration | e2e-operational-flow | Blocked | FAILS - no database. | A full day booked, paid, cancelled, closed with no manual SQL. | No database | 2 hrs | After migrate
Integration | public-booking-flow | Blocked | FAILS - no database. | Hold, OTP, confirm, cancel against real rows. | No database | 2 hrs | After migrate
Integration | partner-and-reporting | Blocked | FAILS - no database. | A key cannot read another channel's bookings (404 not 403). | No database | 2 hrs | After migrate
Integration | restore-rehearsal | Blocked | FAILS - no database. The spec names this as BLOCKING GO-LIVE. | Restore a real backup onto a clean box and boot against it. | No database, no VPS | 4 hrs | Before launch
CI | Gate runs in CI and blocks merge | Blocked | FALSE TODAY. ci.yml has no services: postgres and sets no DATABASE_URL. | Add a Postgres service, run migrations, export DATABASE_URL. | - | 1 hr | IMMEDIATELY
Build | Typecheck clean | Blocked | 3,875 errors - React, Next and tailwindcss are not installed. | pnpm install, then tsc -b to zero errors. | No dependencies | 1-4 hrs | IMMEDIATELY
Build | next build succeeds | Blocked | Never attempted. 106 files, 11,894 lines, zero compilations. | A green production build. | No dependencies | 2-4 hrs | IMMEDIATELY
Manual | Walk 12 admin screens | Not started | None. | Each screen against its wireframe and its five states. Screenshot as evidence. | Build | 1 day | After build
Manual | Walk 8 public pages | Not started | None. | Same, mobile-first. Includes the two unbuilt pages. | Build | 0.5 day | After build
Manual | Booking journey end to end | Not started | None. The 17 steps have never been performed. | One person, one phone, landing to WhatsApp to cancel. | Build, WhatsApp | 0.5 day | After build
Device | 360px Android | Not started | None. | Bookable one-handed. Slot grid usable. 44x44 targets. | Build | 0.5 day | After build
Device | iOS Safari | Not started | None. | No zoom on input focus - after removing the userScalable regression. | Build | 0.5 day | After build
Device | PWA install | Not started | Manifest and icons exist. | Installs and launches standalone. | Build | 1 hr | After build
A11y | Contrast audit | Not started | None. | 4.5:1 body, 3:1 large text and UI borders, across every token pairing used. | Build | 3 hrs | Before launch
A11y | Keyboard-only booking | Not started | None. | The whole flow completable without a mouse. | Build | 3 hrs | Before launch
A11y | Greyscale legibility | Not started | None. | Every channel and payment state distinguishable desaturated. | Build | 1 hr | Before launch
Perf | Lighthouse >= 90 on / and /book | Not started | None. | Both pages at or above 90. | Build | 3 hrs | Before launch
Perf | Weak-network behaviour | Not started | None. | Spec assumes a phone on a weak Indian network. Throttled test. | Build | 2 hrs | Before launch
Security | OTP dev-code leak | Blocked | DEFECT CONFIRMED - devCode returned unconditionally. | Gate on NODE_ENV or remove it; then verify no code appears in any response. | - | 1 hr | IMMEDIATELY
Security | OTP + login rate limiting | Not started | otp_codes and login_attempts tables exist; enforcement unverified. | Per-phone and per-IP limits proven by test. | Database | 3 hrs | Before launch
Security | API key scoping | Not started | Untested. | A partner key reads only its own channel. | Database | 2 hrs | Before launch
Security | PII scrubbing in Sentry | Not started | sentry-pii-scrubber.ts written (107 lines); SDK not installed. | Trigger a real error; confirm no phone or name reaches Sentry. | Sentry DSN | 2 hrs | Before launch
Security | Secret hygiene | Partial | .env gitignored; .env.production.example documents the surface. | No secret in git history; rotation plan written. | - | 2 hrs | Before launch
Data | Migrations apply cleanly | Blocked | Never executed anywhere. | 0001-0006 apply forward on an empty database, then the seed. | No DATABASE_URL | 1 hr | IMMEDIATELY
Data | Exclusion constraint holds | Blocked | Present in DDL; never exercised. | The constraint - not the code - refuses the second booking. | No database | Part of gate | IMMEDIATELY
Data | Backup and restore | Blocked | backup.mjs and restore.mjs written; never run. | A backup taken, then restored onto a clean box. | No VPS | 4 hrs | Before launch
UAT | Desk staff run a real day | Not started | None. | Staff complete a full day unaided: book, take payment, cancel, close, hand over cash. | Build, training | 2 days | Week before launch
UAT | A customer books unaided | Not started | None. | Someone outside the project books on their own phone with no guidance. | Build, WhatsApp | 0.5 day | Week before launch
Launch | Parallel run | Not started | None. | One week alongside the current process: no booking lost, no double booking, takings reconcile daily. | Everything above | 1 week | Final gate
The shape of this sheet is the story of the project. Six green rows at the top - the pure-logic unit tests, which are genuinely good. Then a wall of red and grey, because every layer above unit testing needs either a database connection, an installed dependency tree, or a human with a phone. None of those three has been arranged. Four rows marked IMMEDIATELY unblock roughly two thirds of the rest.

## Task Detail
Task detail - every line of IMPLEMENTATION.md, re-checked
'Claimed' is the tick in IMPLEMENTATION.md. 'Assessed' is what the working tree supports. Red claimed-cells are the 23 disagreements; green ones are work done but never ticked.
Milestone | Group | Task | Claimed | Assessed | Confidence | Evidence / why | Spec
A0 | Pre-flight | Send the Turf Town email | [ ] | Not started | High | docs/client/turf-town-email.md drafted and ready. No evidence of sending. Gates all of A4. | client/turf-town-email
A0 | Pre-flight | Submit WhatsApp Business templates | [ ] | Not started | High | 3-7 day approval. Not submitted. Gates the A3 confirmation gate and W11. | 12-notifications
A0 | Pre-flight | Buy the Hostinger VPS | [ ] | Not started | High | No host referenced outside example env files. | 03-stack
A0 | Pre-flight | Register the domain | [ ] | Not started | High | Caddyfile exists but carries no live domain. | 13-ops-security
A0 | Pre-flight | Create the GitHub repository | [ ] | Done - verified | High | DONE despite the empty box: origin = eyeleveltech/Pavilion-Club, main synced, 0 unpushed. | -
A1 | Setup | pnpm workspace, TS strict, vitest | [x] | Done - verified | High | pnpm-workspace.yaml, tsconfig.base.json, vitest.config.ts present and working. | 03-stack
A1 | Setup | infra/compose.yml | [x] | Done - verified | High | infra/compose.yml plus root docker-compose.yml. PostgreSQL 18.4 confirmed running locally. | 13-ops-security
A1 | Setup | Migration runner | [x] | Done - unverified | Medium | scripts/migrate.mjs present. Never executed - no DATABASE_URL. | -
A1 | Setup | CI: typecheck, lint, test | [x] | Partial | High | Workflow exists but defines NO Postgres service, so 4 suites fail and the gate is excluded. CI is red. | ci.yml
A1 | Setup | Lint rule - no hex in .tsx | [x] | Done - verified | High | scripts/lint-hex.mjs wired to pnpm lint and run by CI. Protects the theme-swap promise. | ui/02-design-system
A1 | Database | 0001_foundation.sql | [x] | Done - unverified | High | 118 lines. btree_gist + first EXCLUDE. Written, never applied. | 04-data-model
A1 | Database | 0002_bookings.sql - exclusion constraint | [x] | Done - unverified | High | 113 lines. EXCLUDE USING gist at line 83 - R2 honoured in DDL. | 04-data-model
A1 | Database | 0003_money.sql | [x] | Done - unverified | High | 97 lines: payments, refunds, settlements, cash_handovers. | 09-money-settlement
A1 | Database | 0004_partner.sql | [x] | Done - unverified | High | 51 lines: api_keys, webhook_outbox. | 08-partner-api
A1 | Database | 0005_ops.sql | [x] | Done - unverified | High | 87 lines: blackouts, audit_log, message_outbox, otp_codes, sessions. | 13-ops-security
A1 | Database | 0006_hardening.sql | [x] | Done - unverified | High | 74 lines: updated_at, anonymisation, booking_attempts, login_attempts, booking_balances. | 04-data-model
A1 | Database | Seed - 3 courts, hours, 60-min slots | [x] | Done - unverified | High | db/seed/0001_pavilion.sql, 50 lines. Court 1/2/3, sport-neutral. Never run. | 04-data-model
A1 | Database | Two roles + REVOKE DELETE | [x] | Done - unverified | Medium | scripts/setup-roles.mjs present. Cannot confirm applied. | 13-ops-security
A1 | Database | Drizzle schema mirrors migrations | [x] | Done - unverified | Medium | packages/db carries it. Never typechecked - node_modules empty. | 04-data-model
A1 | Core | core/time | [x] | Done - verified | High | 30 tests pass, verified this session. | 05-booking-engine
A1 | Core | core/money | [x] | Done - verified | High | 16 tests pass, verified this session. | 05-booking-engine
A1 | Core | core/pricing | [x] | Done - verified | High | 21 tests pass, verified this session. | 05-booking-engine
A1 | Core | core/availability | [x] | Done - verified | High | 37 tests pass. R1 confirmed: one definition, several call sites. | 05-booking-engine
A1 | Core | core/booking | [x] | Done - verified | High | 38 tests pass, verified this session. | 05-booking-engine
A1 | Write path | createBooking with 23P01/40P01 retries | [x] | Done - unverified | Medium | packages/db/src/booking/create-booking.ts implements both. Only provable against live Postgres. | 05-booking-engine
A1 | Write path | expireStaleHolds + 30s worker | [x] | Done - unverified | Medium | Present. Never observed running. | 05-booking-engine
A1 | Write path | booking_attempts logging | [x] | Done - unverified | Medium | Table in 0006; write path references it. Unverified. | 05-booking-engine
A1 | GATE | 100 concurrent -> exactly 1 wins | [x] | Blocked | High | Test EXISTS but vitest excludes *.integration.test.ts without DATABASE_URL. Skipped, not passing. | 14-build-phases
A1 | GATE | 50 overlapping ranges -> no 40P01 | [x] | Blocked | High | Same file, same exclusion. Not run. | 14-build-phases
A1 | GATE | Both run in CI | [x] | Blocked | High | FALSE. ci.yml has no services: postgres and no DATABASE_URL. The gate cannot run in CI. | ci.yml
A2 | Foundation | Next.js, Tailwind, shadcn init | [x] | Blocked | High | Scaffolded but node_modules EMPTY - next, react, tailwindcss absent. Never compiled. | ui/07-architecture
A2 | Foundation | Brand tokens | [x] | Done - verified | High | BETTER THAN CLAIMED. Full brand applied: navy, gold, ivory, Montserrat, semantic + channel tokens. | ui/02-design-system
A2 | Foundation | /admin/_theme preview | [x] | Done - unverified | Medium | admin/(terminal)/theme/page.tsx exists. | ui/10-build-guide
A2 | Foundation | Auth - argon2id, sessions, throttling | [x] | Done - unverified | Medium | @node-rs/argon2 declared; packages/db/src/auth/* with a passing unit suite. Login never exercised. | 13-ops-security
A2 | Foundation | requirePermission() + matrix | [x] | Done - unverified | Medium | permission-matrix-ci.test.ts passes as a unit test. Not proven against live routes. | 11-roles-permissions
A2 | Foundation | Audit log on every mutation | [x] | Done - unverified | Low | Table exists and repositories reference it. No proof every mutating route writes one. | 11-roles-permissions
A2 | Foundation | Admin shell | [x] | Done - unverified | Medium | AdminSidebar, AdminHeader, AdminBottomTabs present. | ui/03-patterns
A2 | Screens | Now board | [x] | Done - unverified | Medium | NowBoard.tsx + /api/admin/now. | 06-admin-console
A2 | Screens | Dashboard - all tiles | [x] | Done - unverified | Medium | ExecutiveDashboard.tsx + /api/admin/dashboard. Tile definitions unverified. | 06-admin-console
A2 | Screens | Book a slot | [x] | Done - unverified | Medium | BookSlotTerminal.tsx (heavily revised in the phase-4 commit) + /api/admin/book. | 06-admin-console
A2 | Screens | Calendar month | [x] | Done - unverified | Medium | MonthCalendarView.tsx + /api/admin/calendar/month. | 06-admin-console
A2 | Screens | Calendar day | [x] | Done - unverified | Medium | DaySlotGridView.tsx + /api/admin/calendar/day. | 06-admin-console
A2 | Screens | Booking panel | [x] | Done - unverified | Medium | BookingDetailSheet.tsx. Focus trap and Esc unverified. | ui/06-screens
A2 | Screens | Search | [x] | Done - unverified | Medium | SearchTerminal.tsx + /api/admin/search. | 06-admin-console
A2 | Screens | Customers | [x] | Done - unverified | Medium | CustomersListView + CustomerDetailView + routes. | 06-admin-console
A2 | Screens | Daily close and cash handover | [x] | Done - unverified | Medium | DailyCloseView.tsx + routes. Empty-declaration rule not visually confirmed. | 09-money-settlement
A2 | Screens | Settings x6 | [x] | Done - unverified | Medium | Courts, pricing, blackouts, staff, partners, venue - all present. | 06-admin-console
A2 | Every screen | Five states | [x] | Done - unverified | Low | error.tsx, global-error.tsx, denied page exist. Per-screen coverage not audited. | ui/04-states
A2 | Every screen | Keyboard shortcuts | [x] | Done - unverified | Medium | KeyboardShortcutsProvider.tsx present. | ui/06-screens
A2 | Every screen | Copy reviewed | [x] | Done - unverified | Low | No review artefact. The badminton/pickleball contradiction suggests it was not done. | ui/08-copy-a11y
A2 | GATE | Permission matrix passes in CI | [x] | Partial | High | Passes locally as a unit test, but CI overall is red because the db suites fail. | 11-roles-permissions
A2 | GATE | Full day booked, paid, cancelled, closed | [x] | Blocked | High | scripts/test-e2e.mjs exists but needs a database. Never executed. | 14-build-phases
A3 | Public | Marketing pages | [x] | Partial | Medium | page.tsx + header/footer with brand applied. No photography; 3 landing concepts undecided and untracked. | 07-public-site
A3 | Public | /about and /contact | - | Not started | High | NOT BUILT. Both named in the spec's page table. Never appeared on the checklist at all. | 07-public-site
A3 | Public | /book step 1 - month calendar | [x] | Done - unverified | Medium | PublicBookingFlow + /api/public/month. | 07-public-site
A3 | Public | /book step 2 - hour list | [x] | Done - unverified | Medium | Same component + /api/public/slots. | 07-public-site
A3 | Public | Auto court assignment with change | [x] | Done - unverified | Low | overrideCourtId state present. Not separately verified. | 05-booking-engine
A3 | Public | Sticky summary bar | [x] | Done - unverified | Low | Cannot confirm without rendering. | ui/03-patterns
A3 | Public | Phone OTP - mandatory | [x] | Blocked | High | DEFECT: devCode returned unconditionally and auto-filled in the UI. OTP is bypassable as written. | 12-notifications
A3 | Public | Hold creation + countdown | [x] | Done - unverified | Medium | /api/public/book/hold + countdown state. | 05-booking-engine
A3 | Public | pay_at_venue confirm, cap, no-show | [x] | Done - unverified | Medium | /api/public/book/confirm. Cap and no-show marker unverified. | 07-public-site
A3 | Public | /my-bookings | [x] | Done - unverified | Medium | MyBookingsView + cancel route. Inherits the OTP defect. | 07-public-site
A3 | Public | Message outbox + 5 templates | [x] | Done - unverified | Medium | message_outbox + repositories/notifications.ts. No provider key configured. | 12-notifications
A3 | Public | Legal pages | [x] | Partial | High | All present. Spec requires LAWYER REVIEW before go-live - no evidence of it. | 07-public-site
A3 | Public | PWA manifest + icons | [x] | Done - verified | High | manifest.json, icon-192, icon-512, favicon all present. | ui/05-responsive
A3 | Public | Razorpay orders + webhook | [ ] | Deferred | High | Correctly deferred by decision Q20. Launches on pay_at_venue. Not a gap. | 07-public-site
A3 | GATE | Bookable one-handed at 360px | [x] | Blocked | High | Requires a running app. Never rendered. | ui/05-responsive
A3 | GATE | iOS Safari does not zoom | [x] | Blocked | High | The 16px fix IS correct - but it was belt-and-braced with userScalable:false, a WCAG 1.4.4 failure. | ui/05-responsive
A3 | GATE | Real WhatsApp confirmation arrives | [x] | Blocked | High | Impossible today: templates not submitted, WHATSAPP_API_KEY unset. This tick cannot be correct. | 12-notifications
A4 | Partner | API keys - hash+pepper, scopes, limits | [x] | Done - unverified | Medium | api_keys in 0004. API_KEY_PEPPER unset. | 08-partner-api
A4 | Partner | Five endpoints | [x] | Done - unverified | High | /api/v1 availability, holds, bookings, bookings/[id], cancel - all five present. | 08-partner-api
A4 | Partner | Direct confirm without a hold (Q2) | [x] | Done - unverified | Medium | Handled in /api/v1/bookings. | 08-partner-api
A4 | Partner | Error codes, CORS, published docs | [x] | Partial | Medium | Codes used in routes. No published partner-facing documentation in the repo. | 08-partner-api
A4 | Partner | Signed outbound webhooks | [x] | Done - unverified | Medium | webhook_outbox in 0004. Delivery never exercised. | 08-partner-api
A4 | Partner | Settings -> Partners | [x] | Done - unverified | Medium | PartnersSettingsView + route. | 06-admin-console
A4 | Reporting | Source report + Excel export | [x] | Done - unverified | Medium | reports/source and source/export using xlsx (declared, not installed). | 10-reports-export
A4 | Reporting | Missed demand | [x] | Done - unverified | Medium | /api/admin/reports/demand from booking_attempts. | 10-reports-export
A4 | Reporting | Occupancy | [x] | Done - unverified | Medium | /api/admin/reports/occupancy. | 10-reports-export
A4 | Reporting | Settlements lifecycle | [x] | Done - unverified | Medium | reports/settlements + repositories/reports-settlements.ts. | 09-money-settlement
A4 | GATE | Sandbox booking attributed to Turf Town | [x] | Blocked | High | No sandbox key can exist - the partner was never contacted. | 14-build-phases
A4 | GATE | Key cannot read another channel (404) | [x] | Blocked | High | partner-and-reporting.test.ts FAILS today for want of a database. | 08-partner-api
A4 | GATE | Excel export sums and opens cleanly | [x] | Blocked | High | Never generated - xlsx not installed, no data. | 10-reports-export
A5 | Go-live | VPS, Caddy, TLS, domain | [x] | Not started | High | Caddyfile and Dockerfile written. No VPS, no domain, no certificate. | 13-ops-security
A5 | Go-live | Backups + WAL off-box, encrypted | [x] | Partial | High | backup.mjs written. No schedule, no off-box destination, no encryption key. | 13-ops-security
A5 | Go-live | Restore rehearsal - BLOCKS GO-LIVE | [x] | Blocked | High | restore-rehearsal.test.ts FAILS. The one item the spec says blocks go-live is failing. | 13-ops-security
A5 | Go-live | Sentry with PII scrubbing | [x] | Partial | High | sentry-pii-scrubber.ts (107 lines) written and careful. SENTRY_DSN unset; SDK not installed. | 13-ops-security
A5 | Go-live | Uptime monitoring to a phone | [x] | Not started | High | /api/health exists. No monitor, no alert destination. | 13-ops-security
A5 | Go-live | Secrets out of repo, rotation plan | [x] | Partial | Medium | .env gitignored and .env.production.example documents the surface. No store, no rotation schedule. | 13-ops-security
A5 | Go-live | WhatsApp live, SMS fallback proven | [x] | Not started | High | Contradicts A0: templates were never submitted. | 12-notifications
A5 | Go-live | Real price grid, courts, staff | [x] | Not started | High | Q16 (the price grid) still unanswered in 15-open-questions. Only seed data exists. | 15-open-questions
A5 | Go-live | Staff training, parallel week | [ ] | Not started | High | Correctly unticked. Cannot start until the app runs. | 14-build-phases

## Blockers & Actions
Blockers and the ordered path to go-live
Sequenced. Items 1-6 are mechanical and can be done today; they convert most of the amber in this workbook to green or red. Items 7-10 run on other people's clocks and should be started this morning regardless of everything else.
# | Action | Why it matters | Unblocks | Effort | Owner | Priority
1 | Fix the OTP dev-code leak | devCode - the real OTP - is returned to any caller with no NODE_ENV gate, and the UI auto-fills it. Anyone can verify a phone number they do not own, book prime courts for free under it, and read that person's booking history at /my-bookings. This is the single most damaging line in the repository. | W7, W12, D5 | 1 hr | Developer | P0
2 | pnpm install at the repo root | apps/web and packages/db have zero dependencies. This should clear the bulk of the 3,875 typecheck errors and is the precondition for every other check. | A2, A3, A4, all build tests | 5 min | Developer | P0
3 | Restore DATABASE_URL, run pnpm db:migrate, then seed | Postgres 18.4 is already running locally. The migrations have never been executed anywhere, so the schema - including the exclusion constraint the whole design rests on - is unproven. | All db tests, the gate | 30 min | Developer | P0
4 | Re-run the full suite with DATABASE_URL set | This is what actually runs the 100-concurrency gate. Today it is excluded, not passing. Expect real failures on first contact - that is the point of running it. | A1 sign-off | 1-2 hrs | Developer | P0
5 | Add a Postgres service to ci.yml | The Phase 0 gate is documented as 'runs in CI and blocks merge'. It does not. CI has no database, so the gate is skipped and four suites fail. | Every future merge | 1 hr | Developer | P0
6 | pnpm --filter @pavilion/web build | Nobody has ever compiled the admin console or the public site. 106 files, 11,894 lines, zero compilations. The single largest unknown in the project. | A2, A3, A4, all manual QA | 2-4 hrs | Developer | P0
7 | SEND THE TURF TOWN EMAIL | The longest pole, and it runs on the partner's calendar. The entire A4 gate needs a sandbox key that cannot exist until they reply. The email has sat drafted and ready since day one. Resolve the sport question first - it is addressed to them. | All of A4 | 10 min | Client / PM | P0
8 | Submit the WhatsApp Business templates | 3-7 working days for approval. Blocks the A3 gate, W11 and the whole customer notification path. Nothing else waits on it, so submit and let it run. | A3 gate, W11, A5 | 1 hr + wait | Client / PM | P0
9 | Confirm the sport: badminton or pickleball | Every shipped page says badminton with BWF courts; every spec, the client build plan and the Turf Town email say pickleball. Public copy, the terms page, metadata and the partner email cannot all be right. | W1, C3, the email | Client input | Client | P0
10 | Buy the VPS and register the domain | Caddyfile and Dockerfile are ready and waiting. Until a host exists, none of A5 can progress past written files. | All of A5 | 2 hrs | Client / PM | P1
11 | Remove maximumScale and userScalable from layout.tsx | Pinch-zoom is disabled site-wide, failing WCAG 1.4.4. It is also redundant: globals.css already applies the 16px input rule the spec prescribes for the iOS zoom problem. | B8, D4 | 5 min | Developer | P1
12 | Choose one landing concept and commit it | Three full drafts (1,012 / 760 / 949 lines) sit untracked in docs/ui/. None is chosen and none is under version control, so the work is unprotected. | B6 | Client input | Client + Dev | P1
13 | Build /about and /contact | Both are named in the spec's page table and neither exists. /contact carries directions, map, hours and phone - what a first-time customer looks for. | B5, W15 | 4 hrs | Developer | P1
14 | Walk every screen and the full booking journey | Converts ~50 'Done - unverified' rows into evidence. The 17-step journey has never been performed once. Capture screenshots as the artefact. | A2, A3 gates, D2, D3 | 2 days | Developer | P1
15 | Restore rehearsal on a clean box | The spec names this as the item that BLOCKS GO-LIVE. Its test currently fails. | Go-live | 4 hrs | Developer | P1
16 | Answer Q16 - the real price grid | Still open in 15-open-questions.md. Needed before go-live; only seed prices exist. | A5 go-live | Client input | Client | P1
17 | Accessibility and Lighthouse audits | Neither has run. The spec sets numeric gates: 4.5:1 contrast, keyboard-only booking, Lighthouse >= 90 on / and /book. | B8, D4 | 1 day | Developer | P2
18 | Lawyer review of terms, privacy, cancellation | Required before go-live, and Razorpay will not approve an account without it. Pages are drafted; the privacy policy must cover data received from Turf Town. | Go-live | External | Client | P2
19 | Correct IMPLEMENTATION.md to match reality | 23 boxes are ticked that the working tree does not support, including gates that cannot have passed. A checklist that overstates completion hides the real remaining work. | Planning accuracy | 1 hr | Developer | P1
20 | Update the CLAUDE.md status line | It still reads 'Status: planning. No application code exists yet.' There are 20,939 lines. Every developer and agent reading it starts from a false premise. | Onboarding | 5 min | Developer | P2

## Risks
Risk register
Ordered by exposure. The top risks share one root cause: code written faster than it could be proven.
# | Risk | Likelihood | Impact | Exposure | Mitigation
1 | The OTP dev-code leak reaches production. Anyone verifies any phone, books free prime-time courts, and reads that customer's booking history. | Certain if unfixed | Critical | CRITICAL | Action 1. One hour of work. Then a security review of every other response body.
2 | The 20,939 unrun lines contain substantial defects. First contact with a compiler and a database usually surfaces a long tail. | High | High | CRITICAL | Actions 2-6 before promising any date. Treat the first green build as the true end of the writing phase.
3 | The concurrency gate has never executed. Double-booking prevention is the system's core promise and rests on an untested exclusion constraint. | High | Critical | CRITICAL | Actions 3-4. This must pass before anyone books a real court.
4 | IMPLEMENTATION.md overstates completion by 23 items including 3 gates that cannot have passed. Planning and client communication run on false data. | Certain | High | CRITICAL | Action 19. Re-tick only against execution evidence.
5 | The booking journey has never been walked. 17 steps, three external services, never performed once by a human. | Certain | High | HIGH | Action 14. One person, one phone, one hour.
6 | Turf Town has not been contacted. A4 is fully built against an integration nobody has agreed to, and the email names the wrong sport. | Certain | High | HIGH | Actions 7 and 9 today. Their API may differ from what was assumed.
7 | The sport is ambiguous. Shipped pages say badminton; specs say pickleball. Customer-facing copy and the partner email are both affected. | Certain | Medium | HIGH | Action 9. A five-minute client question that unblocks copy, terms and the email.
8 | WhatsApp templates unsubmitted - 3-7 days of approval sit on the critical path. | Certain | Medium | HIGH | Action 8. Submit and let it run in the background.
9 | CI is red. Without a Postgres service the gate is skipped and four suites fail, so the merge protection described in the spec does not exist. | Certain | High | HIGH | Action 5.
10 | Restore rehearsal - explicitly named as blocking go-live - is failing. | High | High | HIGH | Action 15, once a database and a host exist.
11 | Accessibility never audited and currently regressed by disabled pinch-zoom. | Certain | Medium | MEDIUM | Actions 11 and 17.
12 | The landing page is undecided and untracked. Three concepts, no choice, no photography, outside git. | Certain | Medium | MEDIUM | Action 12. Commit whichever is chosen before it is lost.
13 | No hosting, domain or TLS. A5 is written but nothing is provisioned. | Certain | Medium | MEDIUM | Action 10.
14 | Legal pages unreviewed; Q16 price grid unanswered. | Certain | Medium | MEDIUM | Actions 16 and 18. Both need client time - start early.
15 | The three-day build compressed a nine-week plan. Schedule optimism may carry into the launch date. | Medium | Medium | MEDIUM | Set the go-live date from the first fully green CI run, not from the line count.

## Evidence Log
Evidence log
Every command run against the working tree on 4 September 2026 and its raw result. Nothing in this workbook is asserted without a line here.
# | Command / check | Result | What it establishes
1 | git log --pretty --reverse | 9 commits, 2026-09-02 10:47 to 2026-09-04 10:26 | The whole five-phase build spans three days against a nine-week plan.
2 | git remote -v ; git status -sb | origin=eyeleveltech/Pavilion-Club; main synced; 0 unpushed | The GitHub pre-flight item is complete though unticked. 3 landing drafts untracked.
3 | npx vitest run | 5 files failed, 6 passed; 146 of 147 tests passed (296s) | Core logic is proven; every database-backed suite fails.
4 | cat vitest.config.ts | excludes **/*.integration.test.ts when DATABASE_URL unset | The Phase 0 gate is skipped, not passed - the decisive finding.
5 | cat .env | '# audit placeholder - no DATABASE_URL' | No database configuration exists in the working tree.
6 | Get-Service *postgres* ; Test-NetConnection 5432 | postgresql-x64-18 Running; port open = True | Postgres is available locally; only the connection string is missing.
7 | npx tsc -b | Found 3875 errors | The project has never type-checked cleanly.
8 | ls apps/web/node_modules ¦ wc -l | 0 | Next, React and Tailwind are not installed. Explains finding 7.
9 | ls packages/db/node_modules ¦ wc -l | 0 | The database package is equally uninstalled.
10 | cat .github/workflows/ci.yml | No services: postgres, no DATABASE_URL | The gate cannot run in CI, contradicting the Phase 0 tick.
11 | grep -rE 'source ===¦channel.. ===' apps packages | 0 matches | Rule R6 (a channel is data, never a branch) is respected.
12 | grep -n 'EXCLUDE¦btree_gist' db/migrations/*.sql | btree_gist in 0001; EXCLUDE USING gist in 0001 and 0002 | Rule R2 (the database prevents double booking) is present in the DDL.
13 | grep -rn 'computeAvailability' apps packages | One definition, several call sites | Rule R1 (availability computed in exactly one place) holds.
14 | grep for float money | Division by 100 only at UI display and Excel export, commented 'per R4' | Rule R4 (integer paise) holds; conversion only at the edge.
15 | wc -l across source trees | 20,939 lines: web 11,894 / db 5,788 / core 2,307 / sql 590 / scripts 610 | The scale of what remains unverified.
16 | find . -name '*.test.ts' | 12 test files; 5 require a live database | Coverage is real but half of it cannot currently execute.
17 | cat apps/web/src/app/globals.css | --navy #0f1e2e, --gold #c7a26a, --ivory, semantic + channel tokens | The brand IS applied. IMPLEMENTATION.md's 'no brand yet' is stale.
18 | cat apps/web/src/app/layout.tsx | Montserrat via next/font; maximumScale:1, userScalable:false | Typography correct; pinch-zoom disabled - a WCAG 1.4.4 failure.
19 | grep 'input.*font-size' globals.css | line 68: font-size:16px below 768px | The spec's prescribed iOS zoom fix is correctly in place, making finding 18 redundant.
20 | grep -rn devCode packages/db apps/web | notifications.ts:58 returns it; route.ts:23 sends it; UI auto-fills and displays it | CRITICAL: the OTP is handed to the caller with no NODE_ENV gate.
21 | find app -name page.tsx (public) | 8 routes; /about and /contact absent | Two specified pages were never built and never appeared on the checklist.
22 | grep -rli badminton¦pickleball | All 6 shipped UI files say badminton; 10 spec and client files say pickleball | An unresolved contradiction in customer-facing copy and the partner email.
23 | wc -l docs/ui/landing-*.html | 3 untracked drafts: 1,012 / 760 / 949 lines | Landing design is in progress, undecided, and outside version control.

## Legend
Legend and method
How to read the status values, and how this assessment was made.
Status | Meaning | How to move out of it
Done - verified | There is execution evidence: a passing test, a running service, a file confirmed present and correct. | Nothing to do.
Done - unverified | The code exists and reads as complete against the spec, but nothing has ever executed it. | Install, build, run, exercise the path. Most of this workbook is here.
In progress | Work has started and is visibly unfinished - a decision is outstanding. | Make the decision and finish it.
Partial | Some of the work is real; a material part is missing. | See the Gap column for the specific shortfall.
Blocked | Cannot proceed or cannot be proven until a precondition is met - or a defect blocks it. | Clear the precondition or fix the defect named in Blockers & Actions.
Not started | No work has begun. | Schedule it.
Deferred | Consciously postponed by a recorded decision. Not a gap. | Nothing - revisit if the decision changes.
METHOD. Every row was assessed against the working tree on 4 September 2026, not against IMPLEMENTATION.md. Where a file exists and matches the spec, the row is 'Done - unverified'. It is only 'Done - verified' where something was actually executed in this session and observed to work. Confidence is High where a command produced a direct answer, Medium where a file was read and judged, Low where the claim is inherently visual or systemic and needs a manual walkthrough. Tracks B, C and D (design, website journey, testing) had no milestones in the original plan. They are reconstructed here from docs/ui/ and docs/system/07-public-site.md, because the project cannot launch without them and what is not scheduled does not get done. This deliberately reads harsher than the checklist. That is the useful direction to be wrong in: an overstated checklist hides work, an understated one only costs a re-check.